## China Storage Group 2
Owner | NOT CHECKOUT | CHECKOUT | DONE | Points
Sony |  |  | Go through the deck Rick has provided | 1
|  |  | Linux, Python, Flask, Cassandra, Elastic Search | 2
|  |  | Nginx, UWSGI, gevent | 2
| Celery, Rabbit MQ, Redis, Zoo Keeper, Splunk, Zabbix, twemproxy |  |  | 6.5
| Directory Service |  |  | 0.5
| Metadata Service |  |  | 0.5
| Storage Service |  |  | 0.5
| Subscription Service |  |  | 0.5
| Crawler Service |  |  | 0.5
| Action Service |  |  | 0.5
| Push Service |  |  | 0.5
Jerry |  |  | Directory Service | 1
|  |  | Metadata Service | 1
|  |  | Storage Service | 1
|  |  | Subscription Service | 0.5
|  |  | Crawler Service | 0.5
|  |  | Action Service | 0.5
|  |  | Push Service | 0.5
|  | Learn about Mock to write test case and have a quick look at Nose of python. try more practices. |  | 3
| Understand how does queue works in the HPCS. Like task queue by celery or message queue by RabbitMQ. |  |  | 3
|  | Familiar with the NoSQL in system. Including using Cassandra, ElasticSearch. |  | 4
| Look through the storage code again maybe this time can have a lot gains. |  |  | 6
Alisa |  |  | Learning the basic knowledge of Python ---the first part of “Core Python Programming, 2nd Edition”. | 6
|  |  | Preliminary understanding our project--- Wiki | 2
|  | Storage Service |  | 3
| Metadata Service |  |  | 2
| Directory Service |  |  | 2
| Using the development environment |  |  | 1
| Action Service |  |  | 1
| Push Service |  |  | 1
| Crawler Service |  |  | 2
| Flask |  |  | 1
|  |  | Total: | 57
Unplanned Tasks
Jerry |  |  | Git Basic Knowledge
Join S17 Plan Meeting
Alisa |  |  | Breakdown "Preliminary..." task
Join S17 Plan Meeting
Setup dev env.
| Cassandra, Elastic Search |  |  | 1
| Nginx, UWSGI, gevent |  |  | 2
| Celery, Rabbit MQ, Redis, Zoo Keeper, Splunk, Zabbix, twemproxy |  |  | 3

## Burn Down Data
Date | Idea Data | Actual Data
| 57 | 57
2014-08-12 | 54 | 57
2014-08-13 | 51 | 57
2014-08-14 | 49 | 57
2014-08-15 | 47 | 57
2014-08-18 | 45 | 54
2014-08-19 | 43 | 47.5
2014-08-20 | 41 | 47.5
2014-08-21 | 39 | 46
2014-08-22 | 36 | 46
2014-08-25 | 33 | 39
2014-08-26 | 30
2014-08-27 | 27
2014-08-28 | 24
2014-08-29 | 21
2014-09-01 | 18
2014-09-02 | 15
2014-09-03 | 12
2014-09-04 | 9
2014-09-05 | 6
2014-09-08 | 3
2014-09-09 | 0

## Backup - Sony
| From Date | To Date | Number of Days | Topic | comments
| 2014-08-12 | 2014-08-12 | 1 | Go through the deck Rick has provided | Reading
| 2014-08-13 | 2014-08-15 | 3 | Linux, Python, Flask, Cassandra, Elastic Search | Reading + Config+Labs
| 2014-08-18 | 2014-08-22 | 5 | Sony OOO(exams)
| 2015-08-25 | 2014-08-26 | 2 | Nginx, UWSGI, gevent | Reading + Config+Labs
| 2015-08-27 | 2014-09-05 | 8 | Celery, Rabbit MQ, Redis , Zoo Keeper, Splunk, Zabbix, twemproxy | Reading + Config+Labs
| 2015-09-08 | 2014-09-12 | 5 | 1. Directory Service | Source Code deep dive
2. Metadata Service
3. Storage Service
4. Subscription Service
5. Crawler Service
6. Action Service
7. Push Service
| 2015-09-15 | TBD | TBD | Looking into QC and fixing defects (which are already fixed) + new defects to be active in sprints | Defect fixes to understand the source.
Comments from Carson: 4 weeks self learning should be 8/12 ~ 9/9; 8/14 is holiday in India; So Item #2 --> 2 days; Item #5 --> 6.5 days; Item #6 --> 3.5 days in the integrated plan

## Backup - Jerry
First we have 7 web services in the drive project. So first step, I'll make clear of the jobs by all the services do, and what is important that how do these
services interact with storage-service. I'll read/understand the code where storage-service interact to other services.
Second step, as we use Mock for the unit-test. I'll learn about Mock to write test case and have a quick look at Nose of python. try more practices.
Third one, Understand how does queue works in the HPCS. Like task queue by celery or message queue by RabbitMQ.
The fourth step, with the NoSQL in system. Including using Cassandra, ElasticSearch.
Then look through the storage code again maybe this time can have a lot gains.

## Backup - Alisa
08/11-08/19: Learning the basic knowledge of Python ---the first part of “Core Python Programming, 2nd Edition”.
08/20-08/26: Preliminary understanding our project.---training PPT + https://rndwiki2.atlanta.hp.com/confluence/display/SWSWP/Team+Infrastructure
08/27-09/07: Insight into our project.--- Project code + the core technology.
About linux, Flask,….,if needed them, I go to learn them.